## Daily Update
Date | Task | Assignee | Status | Remarks
2022-06-15 | Create questions ui change for adding category and label. | Rahul | Verified
| Yojana Integration | Dikshya | Ready for QC
| Inventory Integration | Rahul | Ready for QC
| Question Integration (Create) | Rahul | Ready for QC
| Emergency Integration | Kamala | Ready for QC | integration is in progress
| Create questions api changes for category and label. | Dipak | Dev Completed
| Users Integration | Sudip | In Progress | Ui changed and integration is in progress(role portion),login ui
| Bulk storing all values in local storage. | Kunjan | Ready for QC | fixing dropdown bugs
2022-06-16 | Nagarik Wardpatra Integration | Dikshya | Ready for QC
| Questions View UI | Kamala | Ready for QC | question dispay
| E-Resources Integration (Create, view, edit , delete) | Sudip | Ready for QC
| Adding survey answers in response. | Kunjan | Ready for QC
| Question Integration (Create, edit, delete, view) | Rahul | Ready for QC
| Notice Integration | Dikshya | Ready for QC
| Municipality Profile UI and view, edit integration | Sudip | In Progress
2022-06-17 | Saving initial answers of children question in state after switching form. | Kunjan | Ready for QC
| Fetching Complains | Dikshya | Ready for QC
| Question Integration (Create, view , edit, delete) | Rahul | Ready for QC
| Users Integration (Create, view, edit) | Sudip | In Progress
| Questions View UI with edit delete options/ | Kamala | Ready for QC
| Necessary api changes for question creation and api for complains. | Dipak | Ready for QC
| Digital Directory API | Dipak | In Progress
| News Section View More and Single page UI | Sudip | Verified
| Education/Agriculture/Infrastructure Dashboard UI | Sudip | Verified
| Login UI | Sudip | Ready for QC
2022-06-20 | News Creation UI | Kamala | Ready for QC | woking on fetch all news
| Municipality edit profile UI | Kamala | To Do
| Setting up Smartnagar project in flutter | Prawesh | Dev Completed
| Frontend features quality assurance. | Dikshya | Ready for QC
| Digital directory API | Dipak | In Progress
| Created question answer response (POST RESPONSE) | Kunjan | Ready for QC
| Family health single page UI | Sudip | Ready for QC
| Question view integration | Rahul | In Progress
| Notice api | Dipak | Dev Completed
2022-06-21 | Ward Creation and Ward View UI | Kamala | In Progress
| Digital directory API | Dipak | In Progress
| Family directory single page UI | Sudip | Ready for QC
| Created question answer response (POST RESPONSE) (Option's subquestion and child question response) | Kunjan/Prawesh | Ready for QC
| Multiple File Upload API | Dikshya | Ready for QC
2022-06-22 | VItal Registration UI | Kamala | In Progress
| POST RESPONSE Bugs Fixing | Kunjan/Prawesh | Ready for QC
| Ward Dashbiard | Sudip | Ready for QC
| Testing Digital Directory API | Dipak | In Progress
| Connecting survey and server api. | Dipak | In Progress
| QA fixing front-end and understanding backend coding structure. | Dikshya | Ready for QC
2022-06-23 | Vital Registration UI | Kamala | In Progress
| Global Configuartion Formatter, Testing Digital Directory API, Connecting Surver/Survey api | Dipak | In Progress
| Created question edit api enhancement, description enhancement | Dikshya | Ready for QC
| Created question answer response (POST RESPONSE) (Option's subquestion response) | Kunjan/Prawesh | Ready for QC
| Health Dashboard UI | Sudip | Ready for QC
2022-06-24 | Vital Registration UI | Sudip/Dikshya/Kamala | In Progress
| Sending data to database. | Kunja/ Prawesh | Ready for QC
| Display question of datetype | Kunjan | Ready for QC
| Cleaning code | Sudip | Ready for QC
2022-06-27 | Vital Registration UI | Dikshya/Kamala | Ready for QC
| Storing Answers (Post Response ) to local database. | Kunjan/Prawesh | Ready for QC
| Generate ghar id for each family head and store it in user table. | Dipak | In Progress
| UI Enhancements, Code optimization for speed | Sudip | Ready for QC
| Family health directory single page (edit form, add form.) | Sudip | Open
2022-06-28 | List all data taken by survey in table. | Kunjan/Prawesh | In Progress
| Generate ghar id for each family head and store it in user table. | Dipak | In Progress
| Seperating question types. | Dipak | Ready for QC
| User edit Integration | Kamala | Ready for QC
| Ward Create/Edit Integration | Kamala | In Progress
| Vital Registration API Change | Dikshya | In-Progress
| Family health directory single page (edit form, add form.) | Sudip | In-Progress
| Question Creation/Edit Integration Testing | Rahul | Ready for QC
| QA solve | Sudip | Ready for QC
2022-06-29 | Family directory overall page integration. | Sudip | To Do
| List all data taken by survey in table. | Kunjan | Ready for QC
| Dynamic Form | Prawesh | Ready for QC
| Vital Registration API change | Dikshya | In-Progress
| 1st sprint QA | Dikshya | To Do
| Filter and Search UI in overall family directory page/ QA | Sudip | To Do
| Generate ghar id for each family head and store it in user table. | Dipak | In Progress
| Single page news integration. | Sudip | In Progress
2022-06-30 | Digital Directory (Data representation) | Rahul | Ready for QC
| 1st sprint QA (WEB) | Dikshya | Ready for QC
| Vital Registration API Enhancements | Dikshya | In Progress
| Ward, Users Integration, Create, Edit | Kamala | In Progress
| Static Questions and Dynamic Questions API seperation | Dipak | In Progress
| Single page news integration | Sudip | Ready for QC
| 1st sprint QA (Mobile) | Kunjan | In Progress
| SMS Research | Dipak | In Progress
2022-07-01 | All types of users/wards dashboard separation | Rahul | Ready for QC
| User answer question submission and ghar id generation api. | Dipak | In Progress
| Common field table creation. | Dipak | In Progress
| Send data to server and WIP common forms | Prawesh | Ready for QC
| 1st Sprint Bug Solving | Kunjan | In Progress
| Vital Registration API Enhancements | Dikshya | In Progress
| Create News Integration and Profile integration | Sudip | In Progress
| User role get and Ward fetch . | Kamala | In Progress
| Overall family details page api on the basis of ghar id . | Nirmal | In-Progress
| Banner Upload API | Nirmal | In-Progress
2022-07-04 | News Get from Web (In App) | Kunjan | In Progress
| Banner Upload API, | Nirmal | In Progress
| Family details overall page api | Nirmal | In Progress
| User Creations and Ward related bugs solving | Kamala | In Progress
| Vital Registration API enhancements. | Dikshya | In Progress
| Complains input from app. | Prawesh | In-Progress
| Digital Profiling Integration | Rahul | QC In Progress
| Map Integration | Sudip | In Progress
2022-07-05 | Dynamic Form (Common Fields) | Prawesh | In-Progress
| Family details overall page api | Nirmal | In Progress
| Digital Directory Frontend Integration(Completed) | Rahul | Ready for QC
| Vital Registration API Enhancements(Completed) | Dikshya | Ready for QC
| Ward/Users Frontend Integration | Kamala | Ready for QC
| Banner API Integration | Sudip | In Progress
| Common question and dynamic questions table separation | Dipak | Ready for QC
2022-07-06 | Family details addition API for additional family details.(Pregnant, child details and normal family member create api) | Dikshya | In Progress
| Banner API Integration | Sudip | Ready for QC
| All dashboard login api integration testing. | Kamala | In Progress
| Map Integration | Rahul | Ready for QC
| Family details overall page api | Nirmal | Ready for QC
| Digital Profiling (GET) | Kunjan | Ready for QC
| Login Integration (Public, surveyor, mayor, upamayor) | Prawesh | In-Progress
| News Edit, delete Integration | Sudip | Ready for QC
| Question Import/Export | Nirmal | In-Progress
2022-07-07 | Digital Profiling(GET) | Kunjan | Ready for QC
| Vital Registration Integration in app. | Prawesh | In-Progress
| Question Import/Export | Nirmal | Ready for QC
| Banner API integration edit, news edit. | Sudip | Ready for QC
| Child and pregnancy vaccination api. | Kamala | In Progress
| Vital registration Update api | Dikshya | Ready for QC
| Map Integration | Rahul | Ready for QC
2022-07-08 | Answer submission in database . (Changes in api -static question and dynamic question) | Kunjan | Ready for QC
| Vital registration (POST) | Prawesh | Ready for QC
| Question deleletion API bugs | Dipak | In Progress
| Family head single page api | Nirmal | In Progress
| Map Integration Enhancements. | Rahul | In Progress
| Family details addition API for additional family details.(Pregnant, child details and normal family member create api) | Dikshya | In Progress
2022-07-11 | User creation from ward. (Surveyor, Health Assistant, Ward Secretary) | Sudip | In Progress
| All dashboard ui enhancements with proper permission related functionality only. | Sudip | In Progress
| Static and dynamic question bug. (option question and child question), Label Enhancement | Kunjan | In Progress
| Pagination backend | Kamala | In Progress
| Data filter according to ward and municipality. | Rahul | In Progress
| Family details creation ,edit, delete api. | Dikshya | In Progress
| Conflict resolve, question delete api | Nirmal | In Progress
| Family head api details. | Nirmal | In-Progress
2022-07-14 | User table and answer table finalize with data submission and working on logic to fetch answers fetch api after sumbitted from app. | Nirmal | Ready for QC
| Answer-question response for static and dynamic questions. | Kunjan/Rahul | Reaady for QC
| Overall family details page api. | Dikshya | Ready for QC
| Child and pregnancy vaccination api. | Kamala | Ready for QC
| Banner pagination enhancement, import/export question integration | Sudip | Ready for QC
2022-07-15 | Overall family details page integration | Sudip | Ready for QC
| Family member api, bulk survey data submit (Image is remaining) | Dikshya | Ready for QC
| Bulk user creation api (house id wise) | Dikshya | In Progress
| Single family detail page integration | Sudip | In Progress
| Count API, vaccination api | Kamala | In Progress
| Survey questions enhancements after backend change and answer-question submission in local storage and network database. | Kunjan/Rahul | Ready for QC
| All question answers fetch api after submitted from app | Nirmal | In-Progress
| QA fixing | Rahul | In-Progress
2022-07-18 | User Address Location, User Contact. | Kunjan | Ready for QC
| Fix Issues , MWELL issues | Kunjan/Rahul | In-Progress
| Count API Integration , CHild and Pregnancy Vaccination API | Kamala | In-Progress
| Error handling Implementation, Refactoring. | Nirmal | Ready for QC
| Family directory testing for submitting data. | Nirmal | In Progress
| Navbar profile login integration | Sudip | Ready for QC
| QA Fix | Sudip | In Progress
2022-07-19 | Qa fix of survey question answer submission | Kunjan | In Progress
| COunt API Integration, Child and Pregnancy Vaccination API | Kamala | In-Progess
| Family directory single page all api. | Nirmal | Ready for QC
| ALL modules api enhancement for Created By and Updated BY . | Dikshya | Ready for QC
| Testing data submission api for all survey question-answers | Rahul | Ready for QC
2022-07-20 | ALL DASHBOARD enhancements (Acheive Perfection with user creation and appropriate permissions) | Sudip | In-Progress
| Family member single page api integration on frontend. | Rahul | Ready for QC
| Count API Integration, Child and Pregnancy Vaccination API | Kamala | Ready for QC
| Image Upload from Survey app during submission | Kunjan | In Progress
| Auth Implementation, Bulk answer submissions API, Issue fixing | Nirmal | Ready for QC
2022-07-21 | Family user edit api for single page family details. | Dikshya/Kamala | In-Progress
| User creation from admin, ward creation, ward user creation perfection.( USER AND WARD module should be perfect by tomorrow) | Sudip | In-Progress
| All dashboard perfection (All dashboard should be perfect by tomorrow) | Sudip | Ready for QC
| Image Upload Submission from APP, surveyor and admin login seperation. (Role wise login) | Kunjan/Prawesh | Ready for QC
| Family directory sngle page api integration on frontend. | Rahul | Ready for QC
| API Issue Fixing | Nirmal | In Progress
2022-07-22 | API Issue Fixing and API testing (Survey data submission testing) | Nirmal | Ready for QC
| Image Upload Submission from APP, survey and admin login seperation. (Role wise login) | Kunjan | Ready For App
| All dashboard and user perfection. | Sudip | Ready for QC
| App distribution for production and testing. | Prawesh | Ready for QC
| Family edit api. | Dikshya | Ready for QC
2022-07-25 | Bulk user and bulk image data submission api enhancements. | Nirmal | In-Progress
| Family head and family member edit api integration. | Rahul | In Progress
| Vital registration. | Prawesh | In-Progress
| Validation Error handling and reload . | Kunjan | Ready for QC
| Notifications Required API | Kamala | In-Progress
| Family details create and delete api . | Dikshya | Ready for QC
| Search and Filter API Integration | Sudip | Ready for QC
2022-07-26 | Vital registration Requests (Public APP) | Prawesh | In Progress
| User details get in APP | Kunjan | In Progress
| Vital Registration UI enhancements and integration. | Sudip | Ready for QC
| Notification Setup in server side and API enhancements. | Kamala | In Progress
| Digital Directory API Enhancements. | Dikshya | In Progress
| Bulk user and bulk image data submission API. | Nirmal | Ready for QC
2022-07-27 | User details get in app | Kunjan | In-Progress
| Vital registration request. | Prawesh | In-Progress
| All dashboard filter, user creation from ward integration due to few changes in api. | Sudip | Ready for QC
| Vaccination APi Notification | Kamala | In-Progress
| Question Indexing API | Dikshya | In-Progress
| Create family edit integration | Rahul | Ready for QC
| Digital Directory Api Enhancements. | Nirmal | In-Progress
2022-07-28 | User details get in app. | Kunjan | In Progress
| Vital Registration request. (APP) | Prawesh | In Progress
| Vital Registration Integration (Web) | Sudip | In Progress
| Vaccination Notification API | Kamala | In Progress
| Family head filter ward wise, question indexing api changes, family create api enhancements. | Dikshya | In Progress
| Family create integration | Rahul | In Progress
| Digital Directory API Enhancements. | Nirmal | In-Progress
2022-07-29 | Digital Directory API Enhancements/ Bulk data submission api enhancements. | Nirmal | In Progress
| Change password API | Dikshya | Ready for QC
| Bulk data submission with image. | Kunjan | Ready for QC
| Vital Registration Request EDIT before approval. | Prawesh | In Progress
| Vital Registration Integration | Sudip | In Progress
| Child and pregnancy vaccination notification api | Kamala | In Progress
| Family details create integration testing. | Rahul | In Progress
2022-08-01 | VItal Registration (Birth integration) | Sudip | In-Progress
| Notification Integration (Frontend) | Sudip/Kamala | In-Progress
| Delete api enhancement in all module (Soft delete) | Dikshya | Ready for QC
| Vital Registration API Enhancement. | Kamala | Ready for QC
| Get profile details. | Kunjan | In-Progress
| Digital Directory API Enhancements. | Nirmal | Ready for QC
| Question Indexing Frontend Integration | Rahul | Ready for QC
| Vital Registration Requests) | Prawesh | In-Progress
2022-08-02 | Get family details (Profile) in Public app | Kunjan | In Progress
| Marriage Certifcate (Vital registration request) | Prawesh | In Progress
| Marriage Certificate (Vital registration integration) | Sudip | In Progress
| Vital Registration API Enhancements. | Kamalla | In Progress
| Digital Profiling Integration | Rahul | Ready for QC
| Digital Profiling API Enhancements. | Nirmal | Ready for QC
| Study new project. | Dikshya | In Progress
2022-08-03 | Digital Profiling and Family details get in public app. | Kunjan | In Progress
| Vital registration request | Prawesh | In Progress
| Vital registration Integration | Sudip/Kamala | In Progress
| Vital Registration API Enhancements. | Dikshya | In Progress
| Digital Profiling Ward Filter | Nirmal | In Progress
| Error validation on HMIS | Nirmal | In Progress
| Family directory frontend enhancements. | Rahul | In Progress
2022-08-04 | Family Profile get in app. | Kunjan | In Progress
| Vital Registration Request. | Prawesh | In Progress
| Death Certificate Vital Registration Integration | Kunjan | In Progress
| Vital Registration Image Upload Api enhancement. | Dikshya | In-Progress
| Family directory frontend enhancements. | Rahul | In-Progress
| Notification INtegration Frontend. | Kamala | In-Progress
| Digital Profiling Ward Filter | Nirmal | In-Progress
2022-08-05 | Notification Integration | Kamala | In Progress
| Divorce and Death Vital Registration Integration | Sudip | Ready for QC
| Vital Registration Request. | Prawesh | In Progress
| Push Notification | Kunjan | Ready For App
| Frontend Integration and Authentication in HMIS | Rahul | Ready for QC
2022-08-08 | Change password and forget password in app. | Kunjan | In-Progress
| Vital Registration Request. | Prawesh | In-Progress
| Vital Registration Integration (Migration) | Sudip | Ready for QC
| Notificatin Vaccination Integration | Kamala | Ready for QC
| HMIS Backend (Project Understanding) | Dikshya | In-Progress
| HMIS Authentication Frontend. | Rahul | Ready for QC
| HMIS Swagger Integration | Nirmal | Ready for QC
2022-08-09 | Vital Registration Request (Birth) | Prawesh | In Progress
| Certificate generation and send (Web) Integration | Sudip | In Progress
| Vital Registration Upload api enhancement | Dikshya | In Progress
| Count API Integration | Kamala | In Progress
| Digital Directory Integration enhancement. | Rahul | Verified
| HMIS Swagger Integration and CRUD operations. | Nirmal | In Progress
2022-08-10 | QA Fixing APP | Kunjan | In Progress
| Vital Registration Request. | Prawesh | In Progress
| QA Fixing WEB | Sudip | In Progress
| Notification Integration | Kamala | In Progress
| HMIS Frontend (Auth module) | Rahul | Ready for QC
| HMIS Backend (Validation) | Nirmal | In Progress
2022-08-11 | Yojana Municipality and Ward wise differentiation. | Kunjan | In-Progress
| Wrapping up Vital Registration | Prawesh | In-Progress
| HMIS Code Understanding. | Kamala | In-Progress
| HMIS Code Understanding. | Dikshya | In-Progress
| HMIS User Module Integration | Rahul | In-Progress
| HMIS Filter for Searching. | Nirmal | In-Progress

## 3rd Sprint Backend
Ticket ID | Reference ID | Description | Portal | Asignee | Story Point Estimate (days) | Status | Start Date | End-Date
SNB001 |  | Family details single page create api. (BACK LOG) | Master | Dikshya |  | Ready for QC | 2022.07.25 | 2022.07.25
SNB002 |  | Family details single page, delete api. (BACK LOG) | Master | Dikshya |  | Ready for QC | 2022.07.25 | 2022.07.25
SNB003 |  | Digital Profiling API ENhancements | Master | Nirmal |  | Ready for QC | 2022.07.27
SNB004 |  | Appropriate permissions and authenticity enhancements. | Master | Hemanta |  | To Do
SNB005 |  | Bulk user submission api with image upload. | Master | Nirmal |  | Ready for QC
SNB005 |  | Notification API for Child and Vaccination | Master | Kamala |  | Ready for QC | 2022.07.25 | 2022.07.27
SNB006 |  | Notification API for News. | Master | Kamala |  | Ready for QC | 2022.07.26 | 2022.07.28
SNB007 |  | Question Indexing API | Master | Dikshya |  | Ready for QC
SNB008 |  | Live Chat Application API | Master | Nirmal |  | To Do
SNB009 |  | SMS Sending API for user credentials based on ghar id. | Master | Hemanta |  | Ready for QC
SNB010 |  | Family head edit (Changing family head) api. | Master | Dikshya |  | Ready for QC
SNB011 |  | Forget password api. | Master | Hemanta |  | Ready for QC
SNB012 |  | Profile image Upload api. | Master | Dikshya |  | Ready for QC
SNB013 |  | All type of user edit api. | Master | Hemanta |  | Ready for QC
SNB014 |  | Change Password api. | Master | Dikshya |  | Ready for QC
SNB015 |  | All type of User delete api. | Master | Hemanta |  | Ready for QC
SNB016 |  | Appropriate Error handling enhancements for all kinds of api. | Master | Dikshya |  | To Do
SNB017 |  | ERD Daigram . | Master | Kamala |  | Ready for QC

## 3rd Sprint Frontend
Ticket ID | Reference ID | Description | Portal | Asignee | Story Point Estimated vs Acheived (days) | Status | Start Date | End Date
SNF001 |  | Family details single page create/edit integration. (BACK LOG) | Master | Rahul |  | Ready for QC
SNF002 |  | Family details overall page search/filter integration. (BACK LOG) | Master | Sudip |  | Ready for QC
SNF003 |  | Family details single page delete integration. (BACK LOG) | Master | Rahul |  | In Progress
SNF004 |  | Digital Profiling enhancements. | Master | Rahul |  | Ready for QC
SNF005 |  | Vital Registration Integration | Master | Sudip |  | Ready for QC
SNF006 |  | Certificate generation | Master | Sudip |  | In Progress
SNF007 |  | Yojana Integration for all departments. | Master | Sudip |  | Ready for QC
SNF008 |  | Notification UI for Vaccination . | Master | Sudip |  | Ready for QC
SNF009 |  | Notification INtegration for Vaccination | Master | Kamala |  | Ready for QC
SNF010 |  | Live Chat Integration | Master | Rahul |  | To Do
SNF011 |  | Family head change api integration. | Master | Rahul |  | Ready for QC
SNF012 |  | Question Indexing Integration | Master | Rahul |  | Ready for QC
SNF013 |  | Change password Integration | Master | Rahul |  | To Do
SNF014 |  | Forget password Integration | Master | Rahul |  | To Do
SNF015 |  | All types of user edit integration | Master | Rahul |  | To Do
SNF016 |  | All type of user delete integration | Master | Rahul |  | Ready for QC
SNF017 |  | Profile image upload integration | Master | Rahul |  | To Do
SNF018 |  | SMS Send Integration | Master | Rahul |  | To Do

## 3rd Sprint Mobile
Ticket ID | Reference ID | Description | Portal | Asignee | Story Point Estimate (days) | Status | Start Date | End Date
SNF001 |  | Vital Registration (Backlog) | Master | Prawesh |  | In Progress
SNF002 |  | Bulk Data submission with image upload (Backlog) | Survey | Kunjan |  | Ready for QC
SNF003 |  | Public APP Login | Public APP | Kunjan |  | Ready for QC
SNF004 |  | Survey edit integration after sumbission. | Survey | Kunjan |  | To Do
SNF005 |  | Push Notification for child and pregnancy vaccination | Master | Kunjan |  | Ready for QC
SNF006 |  | Push Notification for news. | Master | Prawesh |  | Ready for QC
SNF007 |  | Live chat application | Messaging | Prawesh |  | To Do
SNF008 |  | Forget password and Change password | Master | Kunjan |  | In Progress
SNF009 |  | Mayor/Upamayor Portal | Master | Kunjan |  | To Do
SNF010 |  | Total Count for how many survey were taken in a day. | Survey | Kunjan |  | To Do
SNF011 |  | Get all informations about family details. | Public APP | Kunjan |  | Ready for QC
SNF012 |  | News Filter by Department. | Public APP | Kunjan |  | Ready for QC
SNF013 |  | Notices created by Municipality | Master | Kunjan |  | Ready for QC

## 3rd Sprint QA
Ticket ID | Description of Issue | WEB/APP | Priority | Asignee | Type | Status
SNQ001 | Ward indication must be more proper. | WEB | High | Rahul | Bug | Open
SNQ002 | APP: Complains: Long description can't be felt. | APP | High | Kunjan | Bug | Open
SNQ003 | Backend: Mobile no uniqueness issue. | API | High | Nirmal | Bug | Open
SNQ004 | APP: Login according to credentials of ghar id. | APP | High | Kunjan | Bug | Open
SNQ005 | Confirm Once: Web: Vital Registration in municipality as well. | Web | High | Sudip | Enhancement | Open
SNQ006 | Confirm Once: Ward Selection: Without Login: Complains. | App | High | Prawesh | Enhancement | Open
SNQ007 | Confirm Once: Push Notification: Design: Inside APP or Outside APP | App | High | Kunjan | Enhancement | Open
SNQ008 | Confirm Once: Push notification for vaccination should be stored. | App | High | Kunjan | Enhancement | Open
SNQ009 | Digital Profiling: Indication should be empty in piechart if there's no data. | App | High | Kunjan | Enhancement | Open
SNQ010 | Confirm Once: Super Admin: Utility payment (Water supply, Cable bill) | WEB | High | Sudip | Enhancement | Open
SNQ011 | Nagarik WardPatra Fetch Bug. | APP | High | Kunjan | Bug | Open
SNQ012 | Municipaliy edit Profile is not working. | Web | High | Sudip | Bug | Open

## 2nd sprint QA
Ticket ID | Description of Issue | WEB/APP | Priority | Asignee | Type | Status
SNQ001 | Family details single page: Option question not displaying properly. | WEB | High | Rahul | Bug | Open
SNQ002 | Digital Profiling functionality. | WEB | High | Rahul | Bug | Open
SNQ002 | Family details single page: All details is not fetched for checkbox details. | WEB | High | Rahul | Bug | Open
SNQ003 | Family details overall page: DOB is in negative. | WEB | Medium | Rahul | Bug | Verified
SNQ004 | Give Ward Number indication in map. | WEB | Low | Rahul | Enhancement | Open
SNQ005 | Proper Error Handling needed on backend for every kinds of api. | WEB | High | Nirmal | Bug | Open
SNQ006 | APPLICATION: Family head proper validaiton needed on app. | APP | High | Kunjan | Bug | Verified
SNQ007 | APPLICATION: Previous data were also submitted while taking new survey. | APP | High | Kunjan | Bug | Verified
SNQ008 | APPLICATION: Reload enhancement for relaoding questions. | APP | High | Kunjan | Enhancement | Verified
SNQ009 | Web: ALL previous data are replaced by the latest data. | WEB | High | Rahul | Bug | Verified
SNQ010 | WEB: Option question bug while creating conditonal drop down and pregnancy condtional drop down. | WEB | High | Rahul | Bug | Open
SNQ011 | Web: Family head edit leads to client side error. | WEB | High | Rahul | Bug | Verified
SNQ012 | Web: Dropdown and checbox options are not fetched while trying to edit. | WEB | High | Rahul | Bug | Open
SNQ013 | APP: Reload validation . | APP | High | Kunjan | Bug | Open
2022-07-30
SNQ013 | Web: Mobile number is not fetched correctly on overall family details page. | WEB | High | Rahul | Bug | Verified
SNQ014 | APPLICATION: Conditional name drop down blank issue. (Delete wala issue) | APP | High | Kunjan | Bug | Open
SNQ015 | Web: Conditional name dropdown not fetched on web. | WEB | High | Rahul | Bug | Verified
SNQ016 | Web: Family head religion is not edited properly. (It becomes 80 as soon as it's updated.) | WEB | High | Rahul | Bug | Verified
SNQ017 | Web: Conditional name dropdown edit is not working. | WEB | High | Rahul | Bug | Open
SNQ018 | Web: Family head caste edit is not working. | WEB | High | Rahul | Bug | Verified
SNQ019 | Web: Unable to add new NCD details. | WEB | High | Rahul | Bug | Verified
SNQ020 | Web: Pregnant Details: Even male names are fetched under condtional name drop down while trying to create new details. | WEB | High | Rahul | Bug | Verified
SNQ021 | Web: Unable to delete any detail. | WEB | High | Rahul | Bug | Open | intregated but api enhancment is remaning
SNQ022 | Web: On every create/edit appropriate parent label should be shown..It displays paribar sadashya in every create/edit. | WEB | High | Rahul | Bug | Verified
SNQ023 | Web: Family head change edit is not working | WEB | High | Rahul | Bug | Verified
SNQ024 | Web: Before adding family head to death detail...add validation as first assign new family head. | WEB | High | Rahul | Bug | Open | later
SNQ025 | Web: Gender, relation, religion, caste edit is not working properly. | WEB | High | Rahul | Bug | Verified
SNQ026 | Web: Ncd details edit : All fields are not fetched. (Here gender is not fetched) | WEB | High | Rahul | Bug | Open
SNQ027 | Web: For every edit, it's shown as family head for every member. | WEB | High | Rahul | Bug | Verified | it will not affect | it will not affect
SNQ028 | Web: Family head change should reflect on overall family details page as well. | WEB | High | Rahul | Bug | Verified
SNQ029 | Web: Unable to create family member, child details. | WEB | High | Rahul | Bug | Verified
SNQ030 | APP: Pregnant Details..all data is not fetched. | APP | High | Kunjan | Bug | Open
SNQ031 | Web: Phone number is not fetched in overall family details as soon as family head is changed. | WEB | High | Dikshya | Bug | Open
SNQ032 | Web: Countwise integration ward and municipality. | WEB | High | Sudip | Bug | Open
SNQ033 | App: Before reloading survey display validation as "Are you sure you want to reload?...All data will be lost." | WEB | High | Kunjan | Enhancement | Open
SNQ034 | Web: Redirect to homepage after login..It's routed to auth route which says page not found | WEB | High | Sudip | Bug | Open
SNQ035 | Web: Remove deleted at and token field on table while displaying family details and users. | WEB | High | Sudip | Bug | Open
SNQ036 | Web: DOB error in updating family members. | WEB | High | Rahul | Bug | Fixed
SNQ037 | WeB: Family head edit change is leading to data loss. | WEB | High | Rahul | Bug | Fixed
SNQ038 | APP: Pregnant Details issue. (Family id is different than actual.) | APP | High | Kunjan | Bug | Open
SNQ039 | Web: While editng details some default values are fetched whether or not some value is selected. | Web | High | Rahul | Bug | Fixed
SNQ040 | Web: Validation on DOB | WEB | High | Rahul | Bug | Fixed
SNQ041 | App: Conditional Name dropdown bug. | APP | High | Kunjan | Bug | Fixed
SNQ042 | Web: Map indication number in admin. | Web | High | Rahul | Bug | Open
SNQ043 | Ward secretary and ward health assistant user creations from Ward | Web | High | Sudip | Bug | Open
SNQ044

## 1st sprint QA
Ticket ID | Description of Issue | Priority | Asignee | Type | Status
SNQ001 | Back button needed inside every module. | High | Sudip | Enhancement | Verified
SNQ002 | Inventory display: Product name spelling. | High | Kamala | Enhancement | Verified
SNQ003 | After creation homepage is unscrollable. (After create) | High | Sudip | Bug | Verified
SNQ004 | File Upload in all modules is not working. | High | Dikshya | Bug | Verified
SNQ005 | Municipality profile edit integration. | High | Sudip | Task | Open | API needed
SNQ006 | (Proper standard login form with validation, logo, slogann, municipality name) | High | Sudip | Task | Verified
SNQ007 | Description UI enhancement in all modules | High | Dikshya | Enhancement | Verified
SNQ008 | Login Validation | High | Sudip | Task | Verified | It doesn't say username is required and invalide username password in case of incorred
SNQ009 | Users creation | High | Kamala | Feature | Verified
SNQ010 | Limited News description needed on card | High | Sudip | Enhancement | Verified
SNQ011 | Different modules Action section enhancement | High | Sudip | Enhancement | Verified
SNQ012 | Description model enhancement. | High | Sudip | Enhancement | Verified
SNQ013 | Nagarik Wardapatra leads to internal server error. | High | Dikshya | Bug | Verified
SNQ014 | It displays as create user in form while editing user. (Check in every edit) | High | Kamala | Enhancement | Verified
SNQ015 | Duplicate data is created while clicking add multiple times. | High | Dikshya | Bug | Verified | frontend issue
SNQ016 | Yojana is not created if long description is input. | High | Dikshya | Bug | Verified | frontend issue
SNQ017 | Single page integration of news page. | High | Sudip | Bug | Verified
SNQ018 | Image preview needed. | High | Dikshya | Enhancement | Verified
SNQ020 | News creation ui should be different with big text editor. | High | Sudip | Bug | Verified
SNQ021 | Question delete | High | Rahul | Task | Verified | from frontend it's is intregated but backend must be done, for now parent question is only deleted.
SNQ022 | Modules is not clicked at once. | High | Sudip | Bug | Verified
SNQ023 | CSS is not shown in browser. | High | Sudip | Bug | Verified
SNQ024 | Log out button is needed on profile navbar and logout integration as well. | High | Sudip | Enhancement | Verified
SNQ025 | User creation is not working | High | Kamala | Bug | Verified | {status: 500, errors: [{code: "ER_NO_DEFAULT_FOR_FIELD",…}], timestamp: "2022-06-29T02:57:36.140Z"} errors: [{code: "ER_NO_DEFAULT_FOR_FIELD",…}] status: 500 timestamp: "2022-06-29T02:57:36.140Z"
SNQ026 | Upload banner in map section (Integration) | High | Sudip | Task | Verified
SNQ027 | Vital Registration UI- Approve and Reject button is needed at the button with rejection message. | High | Kamala | Task | Rejected
SNQ028 | Notice creation is not working. | High | Dipak | Task | Verified | {statusCode: 404, message: "Cannot POST /api/v1/notice", error: "Not Found"} error: "Not Found" message: "Cannot POST /api/v1/notice" statusCode: 404
SNQ029 | Creation: Display validation as Upload file. | High | Dikshya | Enhancement | Verified
SNQ030 | Yojana: Percentage: It can't be negative and excess to 100. | High | Dikshya | Enhancement | Verified
SNQ031 | E-Resources: Attachment and Thumbnail is not fetched. | High | Dikshya | Bug | Verified
SNQ032 | E-Resources: Link should be able to click from web as well. | High | Dikshya | Enhancement | Rejected | It's routed to our own website.
SNQ033 | E-Resources: Unable to update E-Resources. | High | Dikshya | Bug | Verified
SNQ034 | Create/Update: Toastify only once even clicked button multiple times (like once in 5 seconds) | High | Sudip | Enhancement | Verified
SNQ035 | Create/Update: Load type of preview should be shown immediately as soon as create/update button is clicked. | High | Sudip | Enhancement | Verified
SNQ036 | Emergency: Unable to update emergency | High | Dikshya | Bug | Verified
SNQ037 | Emergency: Thumbnail is not fetched. (In every module where is thumbnail it must be previewed after clicking on eye icon) | High | Dikshya | Bug | Verified
SNQ038 | Pagination required whererever necessary. | High | Sudip | Enhancement | Verified
SNQ039 | Irrespective of how many times button is clicked toastify messsage should be shown only once in 5 seconds. | High | Sudip | Enhancement | Verified
SNQ040 | Inventory: File upload issue. | High | Rahul | Bug | Verified
SNQ041 | Replace cross button with delete icon. | High | Sudip | Enhancement | Verified
SNQ042 | User create: All information is not fetched while viewing. | High | Kamala | Bug | Verified
SNQ043 | User Create: Remove unncessary filed while editing. | High | Kamala | Enhancement | Verified
SNQ044 | User Create: Username and email must be unique. | High | Kamala | Bug | Rejected | validation must be from backend
SNQ045 | Parent Question: One more type required as none. | High | Rahul | Enhancement | Verified
SNQ046 | View All Question Button in Question Creation page. | High | Sudip | Enhancement | Verified
SNQ047 | Speed and Code optimization | High | Sudip/Kamala/Rahul | Enhancement | Fixed
SNQ048 | Display Validation as Category already exists if category with same name is created. | High | Rahul | Enhancement | Open | backend needed
SNQ049 | Compulsary confirmation popup message wherever there is delete icon. | High | Dikshya | Enhancement | Verified
SNQ050 | Ward Integration , Create, Edit. | High | Kamala | Feature | Verified | (edit,delete api not available)
SNQ051 | Question Edit: While change option type to dropdown from text ,unrequired option is added as "1." with no option. | High | Rahul | Bug | Verified
SNQ052 | Question Delete: While deleting child question , all questions are lost and recovered only after reloading the page. | High | Rahul | Bug | Verified
SNQ053 | Question Create: While creating child question, if category is not selected it displays as something went wrong...display validation as category is required | High | Rahul | Bug | Verified
SNQ054 | Image Preview: UI is overlapped while previewing the image | High | Sudip | Bug | Verified
SNQ055 | No validation is required while updating. | High | Dikshya | Enhancement | Verified
SNQ056 | Options input is available even when type is none. | High | Rahul | Bug | Verified
SNQ058 | Notice : While closing modal of notice , it leads to client side error. | High | Dikshya | Bug | Verified
SNQ059 | News delete, edit integration. | High | Sudip | Task | Verified
SNQ060 | Digital Directory: Option question and child question label is not working. (API Issue) | High | Dipak | Bug | Verified
SNQ061 | Question delete is not working (API ISSUE) | High | Dipak | Bug | Verified
SNQ063 | Ward creation is not working. | High | Kamala | Bug | Verified
SNQ064 | User creation is not working. (It says no permission to create users) | High | Kamala | Bug | Verified
SNQ065 | Popup message is needed on question deletion. | High | Sudip | Enhancement | Verified
SNQ067 | Replace Passwords as Password | High | Kamala | Bug | Verified
SNQ068 | Question deletion is not working (API ISSUE) | High | Dipak | Bug | Verified
SNQ069 | Admin: User creation: Remove admin, house_owner, house_member, surveyor, ward_president, ward_secretarty and ward_health from roles. | High | Sudip | Task | Verified
SNQ070 | Admin: Ward creation: Remove every role except ward president. (Ward president should be by default..no other options to choose role.) | High | Sudip | Task | Verified
SNQ071 | Option question edit/delete is not available. | High | Sudip | Task | Verified
SNQ072 | User/Ward create: After creating user, if try to immediatley create another user without reloading the webpage it leads to client side error. | High | Sudip | Bug | Verified
SNQ074 | User/Ward create: display validation in case of duplicate data where unique data is required. | High | Sudip | Bug | Rejected | bakcend
SNQ075 | OPtion question: Dropdown number- It displays as 1. 1. 1. ..it must be properly indexed. | High | Sudip | Bug | Verified
SNQ076 | Other departments: Restrict to click on ward. | High | Sudip | Bug | Verified
SNQ077 | Ward department proper integration is required. | High | Sudip | Bug | Verified
SNQ078 | Admin: Users: Unnecessary user in form of ward is fetched. | High | Sudip | Bug | Open | api needed
SNQ079 | Ward Portal : Users: unwanted users are fetched in ward. | High | Sudip | Bug | Open | api needed
SNQ080 | Ward Portal;: User creation is not working. | High | Sudip | Bug | Open
SNQ081 | Ward Portal : Don't give excess to survey questions/news creation | High | Sudip | Bug | Rejected | It can go through routes
SNQ082 | Other portals can't update delete notices , news and other features not added by them. | High | Sudip | Bug | Open | backend needed
SNQ083 | Inventory dashboard needed. | High | Sudip | Enhancement | Verified
SNQ084 | All questions are lost when question is deleted...and it's reloaded only after refreshing the page. | High | Rahul | Open | Open
SNQ085 | Question Deletion BUG | High | Nirmal | Bug | Open
SNQ086 | Duplicate data validation message in every module. | High | Nirmal | Bug | Open
SNQ087 | Application client side error as soon as yojana is created. | High | Sudip | Bug | Rejected
SNQ088 | Ward Creation: Mobile number should just be able to input in number. | High | Sudip | Enhancement | Verified
SNQ089 | Admin Users: Remove Caste while displaying. it's not needed. | Low | Sudip | Enhancement | Verified
SNQ090 | Admin Users/ Ward Users / Admin Wards: Only necessary user should be fetched on each table. | High | Sudip | Bug | Open
SNQ091 | Application client side error as soon as e-resource is created. | High | Sudip | Bug | Rejected
SNQ092 | It's taking so much of time to create e-resource, yojana and any other modules. | High | Sudip | Bug | Open
SNQ093 | Validation needed for uniquness error in every module. | High | Sudip | Bug | Open
SNQ094 | Yojana file preview needed while uploading | High | Sudip | Enhancement | Open
SNQ095 | Unable to update yojana/e-resource . Check in every module once. | High | Sudip | Bug | Open
SNQ096 | News filter is not working. | High | Sudip | Bug | Open
SNQ097 | Pagination is needed on news. | High | Sudip | BUg | Open
SNQ098 | News added by admin should be displayed on lhs . In rhs , news added by department should be viewed. | High | Sudip | Bug | Open
SNQ099 | Yojana not created from department dashboard. | High | Sudip | Bug | Open
SNQ100 | Ward all details is not displayed on table. | High | Sudip | Enhancement | Open
SNQ101 | File upload and attachment is not compulsary in modules. | High | Sudip | Bug | Open
SNQ102 | Yojana filter needed according to admin and department. | High | Sudip | Bug | Open
SNQ103 | Admin: Ward Creation: Include President Name (Field) | High | Sudip | Bug | Open
SNQ104 | Notice: remove deleted at . | High | Sudip | Bug | Open

## 2nd Sprint Frontend
Ticket ID | Reference ID | Description | Portal | Asignee | Story Point Estimate (days) | Status | Start Date | Remarks | Dependency | Address to
SNF001 |  | Differentiating Ward and Municipality | Master | Rahul | 0 | Ready for QC | 2022-06-29 | completed
SNF002 |  | Ward Create Integration | Master | Kamala |  | Ready for QC
SNF003 | SNF002 | Ward View, Edit Integration | Master | Kamala |  | Ready for QC
SNF004 |  | Differentiating all type of user dashboard with appropriate credentials | Master | Rahul | 0 | Ready for QC | 2022-06-29 | completed
SNF005 |  | Data representation (Digital Directory) - All answer submitted by surveyor must be represented on form of pie chart and bar diagram on web according to their respective category. | Master | Rahul |  | Ready for QC | 2022-06-29 | completed
SNF006 |  | Family details Overall Page: Family details must fetch on basis of ghar id and family head and all necessary fields needed on overall family detail page. | Master | Sudip |  | Ready for QC
SNF007 | SNF006 | Search needed according to filter on overall family details page. | Master | Sudip |  | Ready for QC
SNF008 |  | Family details Single Page: All data and informations taken by surveyor related to family and family members must be viewed on single page appropriately. | Master | Rahul |  | Ready for QC
SNF009 | SNF008 | Admin must be able to add additional details about family members from web itself. | Master | Rahul |  | Ready for QC
SNF010 | SNF008 | Admin must be able to edit all available informations about family and family members in web itself. | Master | Rahul |  | Ready for QC
SNF011 | SNF008 | Admin must be able to delete family member in case of necessity with confirmation popup message. | Master | Rahul |  | In Progress
SNF012 |  | Map Integration | Master | Rahul |  | Ready for QC | filter data on the basis of ward is remaining, need changes in api
SNF013 |  | Data must be filtered appropriately among ward and municiipality with appropriate permissions. | Master | Sudip |  | Ready for QC
SNF014 |  | All type of dashboard must have only allowed data and modules that's permitted to them according to requirement like health dashboard should have access to health realted data and create news related to health. | Master | Sudip |  | Ready for QC
SNF015 |  | Count Integraton according to required data fields. | Master | Sudip |  | Ready for QC
SNF016 |  | Logo, name, slogan needs to fetch in login form, header section. | Master | Sudip |  | Ready for QC

## 2nd Sprint Backend
Ticket ID | Reference ID | Description | Portal | Asignee | Story Point Estimate (days) | Status | Start Date | Remarks | Dependency | Address to
SNB001 |  | Data representation (Digital Directory) API for all types of answers. | Master | Dipak |  | Ready for QC | 2022-06-29
SNB002 |  | User answer question submission and ghar id generation api. | Master | Dipak |  | Dev Completed
SNB003 |  | Common field table creation. | Master | Dipak |  | Dev Completed
SNB004 |  | Banner Upload API | Master | Nirmal |  | Ready for QC
SNB004 |  | Count API like total population, male, female , child, pregnancy , death counts as well as data directory counts | Master | Kamala |  | Ready for QC
SNB005 |  | Question Import/Export | Master | Nirmal |  | Dev Completed
SNB006 |  | Family details Overall Page API on the basis of houseid including all necessary fields. | Master | Dikshya |  | Dev Completed
SNB007 |  | Search and Filter API in family details Overall Page. | Master | Dikshya |  | Ready for QC
SNB008 |  | Family details single Page API for fetching all informations and data realted to family head and family. | Master | Nirmal |  | Dev Completed
SNB009 |  | Family details single Page API for fetching all informations related to family member. (Child, pregnant, normal member) | Master | Nirmal |  | Dev Completed
SNB010 |  | Family details addition API for additional family details.(Pregnant, child details and normal family member create api) | Master | Dikshya |  | Ready for QC
SNB011 |  | Family details edit API for updating current details. | Master | Kamala |  | To Do
SNB012 |  | Family details delete API for deleting current family member. | Master | Dikshya |  | To Do
SNB013 |  | Pregnancy vaccination and child vaccination api (Dynamic detail fetch) | Master | Kamala |  | Ready for QC
SNB014 |  | Data Filter API according to municipality and ward with appropriate permissions. | Master | Hemanta |  | Dev Completed
SNB015 |  | Surveyor Creation API with appropriate ward and municipality. | Master | Hemanta |  | Dev Completed
SNB016 |  | Routes wise authentication | Master | Hemanta |  | Dev Completed
SNB017 |  | Bulk User Submission API | Master | Dikshya |  | In-Progress

## 2nd Sprint Mobile
Ticket ID | Reference ID | Description | Portal | Asignee | Story Point Estimate (days) | Status | Start Date | Remarks | Dependency | Address to
SNM001 |  | Form validation for compulsary fields and data types. | Survey | Kunjan |  | Ready For App | 2022-06-29
SNM002 |  | Digital Directory. (Data presentation) (GET from WEB) | Survey | Kunjan |  | Ready for QC
SNM003 |  | Image upload/ GPS location in survey app | Survey | Prawesh |  | Ready for QC
SNM004 |  | Count for how many survey has been taken today according to surveyor | Survey | Kunjan |  | To Do
SNM005 |  | Surveyor Login Integration | Survey | Kunjan |  | Ready for QC
SNM006 |  | Public App login Integration according to provided gharid and password. | Public App | Prawesh |  | Ready for QC
SNM007 |  | Vital Registration Integration | Public App | Prawesh |  | In Progress
SNM008 |  | Complain Integration | Public App | Prawesh |  | Ready for QC
SNM009 |  | News and Notice Integration | Public App | Kunjan |  | Ready for QC
SNM010 |  | E-Resources Integration (GET from Web) | Public App | Kunjan |  | Ready for QC
SNM011 |  | Yojana Integration (GET from Web) | Public App | Kunjan |  | Ready for QC
SNM012 |  | Agriculture/Health/Infrastructural/Sports and educational News Integration (GET from WEB) | Public App | Kunjan |  | Ready for QC
SNM013 |  | Emergency services Integration (GET from WEB) | Public App | Kunjan |  | Ready for QC
SNM015 |  | Nagrik Wadapatra Integration (GET from WEB) | Public App | Kunjan |  | Ready for QC

## 1st Sprint Backend
Ticket ID | Reference ID | Title | Description | Portal | Type | Asignee | Story Point Estimate | Status | Start Date | Remarks | Dependency | Address to
SNB001 |  | authentication/authorization |  | Master | Task | Hemanta |  | Dev Completed | 2021-06-09
SNB002 |  | Bulk insert question/answers. |  | Master | Feature | Deepak |  | Dev Completed | 2021-06-13
SNB003 |  | category wise question creation |  | Master | Feature | Deepak |  | Dev Completed | 2021-06-14
SNB004 |  | Category wise question display |  | Master |  |  |  | Dev Completed
SNB005 |  | Question wise count api |  | Master |  |  |  | Dev Completed
SBB006 |  | Ward creation and ward member role |  | Master | Task | Hemanta |  | Dev Completed
SBB007 |  | Category wise question count api |  | Master | Feature | Deepak |  | Dev Completed
SBB008 | SNB001 | User Logout |  | Master | Task | Hemanta |  | Dev Completed
SBB009 |  | Generate ghar id for each family head and store it in user table. |  | Master | Feature | Deepak |  | Dev Completed

## 1st Sprint Frontend
Ticket ID | Reference ID | Title | Description | Portal | Type | Asignee | QA Story Point Estimate (days) | Status | Start Date | Remarks | Dependency | Address to
SNF001 |  | Differentiating ward and municipality. | Proper authentication and authorization should be present for login of ward and municipality with appropriate permissions. | Master | Feature | Hemanta |  | Ready for QC
SNF002 | SNF001 | Login Integration | Proper login with necessary validations differnetiating ward and municipality. | Master | Feature | Hemanta |  | Verified
SNF003 |  | Questions creation integration | Admin should be able to create dynamic questions. | Master | Feature | Rahul |  | Verified
SNF004 | SNF003 | Questions display integration | Admin should be able to view all created questions with proper functioning delete, edit. | Master | Feature | Rahul |  | Verified
SNF005 |  | Users integration | Admin should be able to create all type of users. | Master | Feature | Sudip |  | Ready for QC
SNF006 | SNF005 | User display, edit | Admin should be able to view all created users with proper fucntioning delete, edit options. | Master | Feature | Sudip |  | Ready for QC
SNF007 |  | Ward Integration | Admin should be able to create wards with necessary validation and appropriate fileds. | Master | Feature | Hemanta |  | Ready for QC
SNF008 | SNF007 | Ward View, Edit | Admin should be able to view all created wards with proper fucntioning delete, edit options. | Master | Feature | Hemanta |  | Ready for QC
SNF009 |  | Yojana Integration | Admin should be able to add yojanas with necessary validations and appropriate fileds. | Master | Feature | Dikshya |  | Verified
SNF010 | SNF009 | Yojana View, Edit, Delete | All created Yojana must be viewed and all informations must be fetched with edit/delete options. | Master | Feature | Dikshya |  | Verified
SNF011 |  | E-Resources Integration | Admin should be able to add e-resources with necessary validations and appropriate fileds. | Master | Feature | Sudip |  | Verified
SNF012 | SNF011 | E-Resource View, Edit, Delete | All created E-Resources must be viewed and all informations must be fetched with edit/delete options. | Master | Feature | Sudip |  | Verified
SNF013 |  | Inventory Integration | Admin should be able to add inventories with necessary validations and appropriate fileds. | Master | Feature | Rahul |  | Verified
SNF014 | SNF013 | Inventory View, Edit, Delete. | All created inventory must be viewed and all informations must be fetched with edit/delete options. | Master | Feature | Rahul |  | Verified
SNF015 |  | Emergency Integration | Admin should be able to add emergency services with necessary validations and appropriate fileds. | Master | Feature | Kamala |  | Verified
SNF016 | SNF015 | Emergency View, Edit, Delete | All created Emergency services must be viewed and all informations must be fetched with edit/delete options. | Master | Feature | Kamala |  | Verified
SNF017 |  | Nagarik Wardapatra | Admin should be able to create nagarik wardapatra with necessary validations and appropriate fields. | Master | Feature | Dikshya |  | Verified
SNF018 | SNF017 | Nagarik Wardapatra View, Edit, Delete | All created Nagarik wardapatra must be viewed and all informations must be fetched with edit/delete options. | Master | Feature | Dikshya |  | Verified
SNF019 |  | Notice Integration (Create) | Admin should be able to create nagarik wardapatra with necessary validations and appropriate fields. | Master | Feature | Dikshya |  | Verified
SNF020 | SNF019 | Notice View, Edit, Delete | All created notices must be viewed and all informations must be fetched with edit/delete options. | Master | Feature | Dikshya |  | Verified
SNF021 |  | News Integration | Admin should be able to create news with necessary validations and appropriate fields. | Master | Feature | Kamala |  | Verified
SNF022 | SNF021 | News View, Edit, Delete | All created news must be viewed and all informations must be fetched with edit/delete options. | Master | Feature | Kamala |  | Verified
SNF023 |  | Complains Fetch | All complains added by public must fetch on admin portal. | Master | Feature | Dikshya |  | Verified
SNF024 |  | Differentiating all user dashboard and login integration | Different sets of users must be separated and should login in their own respective dashboard. | Master | Feature | Rahul |  | Verified

## 1st Sprint Mobile
Ticket ID | Reference ID | Title | Description | Portal | Type | Asignee | Story Point Estimate | Status | Start Date | Remarks | Dependency | Address To
SNM001 |  | Questions fetch | All dynamic questions created by users must be displayed appropriately. | Survey |  | Kunjan |  | Verified
SNM002 |  | Question storage | All questions and answers must be stored properly. | Survey |  | Kunjan |  | Ready for QC
SNM003 |  | Login functionality integration | Surveyors should be able to login. | Survey |  | Kunjan |  | To Do
SNM004 |  | Network storage | All answesrs must be stored in database as soon as it;s uploaded on database. | Survey |  | Kunjan |  | Ready for QC

## 1st Sprint Design
Ticket ID | Reference ID | Title | Description | Priority | Portal | Type | Asignee | Story Point Estimate | Status | Start Date | Remarks | Dependency | Address To
SND001 |  | Question creations UI | It should be in different tabs for parent , child and option question with user friendliness. | High | Master | Task | Sudip |  | Verified
SND002 | SND001 | Qestion display UI | All created questions should be displayed with edit/delete option as similar to displayed in app with pop up confirmation message for question deletion. | High | Master | Task | Kamala |  | Verified
SND003 |  | User Creations Form | There should be user creation form with validation for compulsary fields. | High | Master | Task | Sudip |  | Verified
SND004 | SND003 | Created users display | All created users should be displayed with edit/delete option with popu up confirmation message for user deletion. | High | Master | Task | Kamala |  | Verified
SND005 |  | Ward Creations | Ward creation form with validation for compulsary fileds. | High | Master | Task | Sudip |  | Verified
SND006 | SND005 | Ward creations display | Create ward mut be displayed with edit option. | High | Master | Task | Kamala |  | Verified
SND007 |  | Municiaplity Profile UI | Municipality profile can be viewed and details can be updated. | High | Master | Task | Sudip |  | Verified
SND008 |  | Digital Profiling UI | Category wise question data should be displayed in form of pie chart and bar diagram both. | High | Master | Task | Sudip |  | Verified
SND009 |  | Family health folder UI | All public user information must be displayed with ghar id and family head and it must be dispayed on detail while clicked on view button. | High | Master | Task | Kamala |  | Verified
SND010 |  | Proper Modules icon | All modules should have porper icon. | High | Master | Task | Sudip |  | Verified
SND011 |  | All modules UI | All modules should have proper forms and presentation with appropriate fileds. | High | Master | Task | Kamala |  | Verified
SND012 |  | Login UI | Login form for ward and municipality. | High | Master | Task | Sudip |  | Verified
SND013 |  | Edu/Ag/Infr. Dashboard UI | Dashboard UI of educational /agriculture and infrastructure UI | High | Master | Task | Sudip |  | Verified
SND014 |  | News Section Single page and View More UI | News added by municipality must be viewed here and single page news with all details must fetch in single page | High | Master | Task | Sudip |  | Verified
SND015 |  | Vital Registration UI | Vital Registration UI for all portals. | High | Master | Task | Kamala |  | In Progress
SND016 |  | Health Dashboard | Dashboard UI of health portal. | High | Master | Task | Sudip |  | In Progress
SND017 |  | Single page UI of family health directory | Single page UI of family health directory. | High | Master | Task | Sudip |  | Verified
SND018 |  | Single page UI of family health directory (Detailed) | Edit form, add form needed., pregnancy and infant vaccination view page needed | High | Master | Task | Sudip |  | In Progress

## Sprints
Week 1 | Tasks | Sub-tasks | Backend |  |  | Frontend |  |  | App Development
|  |  | Assigned | Status | Remarks | Assigned | Status | Remarks | Assigned | Status | Remarks
1st Sprint (13th June-28th June) | Questions Creations |  | Dipak |  |  | Rahul |  |  | Kunjan
| Questions Edit |  | Dipak |  |  | Rahul |  |  | Kunjan
| Questions Creations integrations |  | Dipak |  |  | Rahul |  |  | Kunjan
| Annswers presentation |  | Dipak |  |  | Rahul |  |  | Kunjan
| User Creations/ Authentications |  | Dipak |  |  | Rahul |  |  | Kunjan
Ghar ID/ SMS for credentials
| UX/UI of Data Presentations |  |  |  |  | Kamala |  |  | Kunjan
| UX/UI of Family Directory |  |  |  |  | Sudip |  |  | Kunjan
2nd Sprint | Data Presentation |  | Dipak | Completed |  | Rahul, Dikshya, Sudip, Kamala |  |  | Kunjan, Prawesh
(28th June- 15th July) | Credentials send to GharID (SMS API) |  | Dipak |  |  | Rahul, Dikshya, Sudip, Kamala |  |  | -
| News and Notifications |  | Dipak | Completed |  | Dikshya |  |  | Kunjan, Prawesh
| E-resources |  |  |  |  | Dikshya |  |  | Kunjan, Prawesh
| Nagrik Wardpatra |  |  |  |  | Kamala |  |  | Kunjan, Prawesh
| Inventory |  |  |  |  | Sudip |  |  | Kunjan, Prawesh
| Emergency Services |  |  |  |  | Kamala |  |  | Kunjan, Prawesh
| Yojana |  |  |  |  | Kamala |  |  | Kunjan, Prawesh
| Complaints |  |  |  |  | Sudip |  |  | Kunjan, Prawesh

## users
UI/UX- Kamala,Sudip
FrontEnd- Rahul,Sudip,Kamala,Dikshya,Hemanta
Backend- Hemanta,Deepak,Dikshya
QA/DevOps- Sandesh
Mobile App- Kunjan,Prawesh,Rahul